P114 – GAMIFIED LEARNING FOR EVERYONE

Revised Project Outcomes Report | AY2026–27

1. Prior results – achieved / artifact-observed

AY2025–26 progressed from a Telegram learning-bot concept toward an Edu Mentor AI offline-first educational platform.

The inspected repository snapshot contains FastAPI, SQLite, local Ollama integration, retrieval/content services, Tamil/English syllabus files, quizzes, progress interfaces and Telegram components.

These artifacts demonstrate implementation evolution, but do not establish successful disconnected operation, curriculum correctness, learning benefit or accessibility/child-safety conformance.

2. Earlier draft claims – not verified

MVP records reported 8 users, 1.8–2.5 s response time, ~88% answer relevance, 100% offline stability and 86% satisfaction.

Final records reported 10 users, 85% task completion, ≥90% response accuracy and 100% quiz accuracy.

These remain team-reported preliminary observations because raw timings, reference sets, instruments, case outputs and valid participant evidence were not supplied.

3. Unresolved gap

The PoC source is missing; authorship/identity and participant/consent records require reconciliation. The eight- and ten-user cohorts have no crosswalk.

Curriculum provenance, expert answer evaluation, low-end-device testing, reproducible build/testing and controlled learning-outcome evidence remain incomplete.

Foreign prototype metrics and contaminated/non-project evidence must remain excluded.

4. Material advancement proposed for AY2026–27

Move from prototype description to controlled validation: version curriculum sources, freeze the evaluated software/configuration, evaluate answer and quiz quality case-by-case, test offline/device behaviour, and establish reproducible project-authored tests.

After required ethics, consent, assent, school permission, privacy and safeguarding approvals, conduct usability first and learning evaluation only with a prespecified comparator and pre/post instrument.

5. Intended measurable outcomes

Curriculum-grounded answer quality; retrieval/grounding, relevance, correctness, readability and language quality; quiz validity; device resource use and latency; usability; and, if approved, pre/post learning and retention outcomes.

6. Next milestones

Freeze evidence and software version → complete curriculum/metric dictionary and expert cases → run technical/device validation → complete required ethics and safeguarding approvals → conduct approved human evaluation → regenerate manuscript values only from retained raw evidence.

Evidence basis

Evidence IDs: P114-C01–C08; repository commit 560a858a2fae7af52d940bf9f824f69db578c230. Status: developmental; reported numerical values are not verified results.